## Sheet1
Note: After completing the form, print to attach to scope. To print for scope attachment, filter to show only tasks identified as "Yes" and size the rows to accommodate the Project Specific Comments.
PROJECT NAME (CIP# XXXXXX-XXXXXX)
Task # | Task | Task Needed | Consultant | City of Columbus | If Authorized | Mod # | Project Specific Comments | Task Description
1 | Project Management | Yes | X
1.1 | Meetings | Yes | X | X |  |  |  | Monthly progress meetings
1.2 | General Oversight | Yes | X
1.3 | QA/QC for limited review | Yes | X |  |  |  |  | Consultant needs to field verify plans with Design Project Manager to confirm existing conditions.
1.4 | Schedule | Yes | X |  |  |  |  | Includes monthly updates
2 | Environmental Documentation | Yes | X | X
2.1 | Ecological Survey Report | Unlikely | X |  | X |  |  | Field verify ecological resources identified during the Planning Phase (PL), collect data on ecological resources with the potential area, and predict ecological impacts. Conduct all field surveys and impact assessments in accordance with the most recent version of the ODOT Ecological Manual. The project type and the anticipated impacts to ecologic resources in the project area will determine the type of ecological survey: Level 1, Level 2 or Level 3.
2.2 | Environmental Site Assessment Screening | Unlikely | X |  | X |  |  | Projects require an ESA Screening if they have right-of-way take and/or deep excavation (greater than 3 feet). The purpose of the ESA Screening is to identify all parcels (sites) within a study area and provide sufficient investigation to develop a list of suspect properties which will require a Phase I ESA. Gathering and reviewing regulatory databases, as well as present and historic land use, information for each site is the primary focus in an ESA Screening. All properties within the project study area are screened at this level. Complete ESA screening for sites within the feasible alternatives to identify properties to be studied further in a Phase I ESA. Document the results of the survey on ODOT’s Environmental Site Assessment Screening Checklists and compile into an ESA Screening Report, prepared in accordance with ODOT’s ESA Guidelines.
2.3 | Phase I Environmental Site Assessment | Unlikely | X |  | X |  |  | In general, the Phase I ESA should not be conducted without having performed an ESA Screening. The ESA Screening deals with all sites within a project area. The Phase I ESA involves only the suspect sites in the project. Prepare a Phase I ESA as needed. All sites evaluated in the ESA Screening and recommended for Phase I ESA work must be approved by the Department before work is started. The intent of the Phase I ESA is to determine the potential of encountering hazardous substances or petroleum products from a specific property. The Phase I ESA involves researching and reviewing site-specific information in order to determine a list of suspect sites which require a Phase II ESA.
2.4 | Phase II Environmental Site Assessment | Unlikely | X |  | X |  |  | Through intrusive sampling and testing of soils and/or groundwater, a Phase II ESA is used to determine the presence or absence of contamination on suspect sites identified in the Phase I ESA. Prepare in accordance with the ESA Guidelines. This assessment can also be used to determine the nature and extent of contamination on a site with a known contamination issue.
2.5 | 401/404 Permitting | Unlikely | X |  | X
3 | Survey and Right of way | Yes | X
3.1 | Project Control, Benchmarks, and Reference Points | Yes | X
3.2 | Base Mapping (incl. field verify.) | Yes | X |  |  |  |  | Consultant to prepare exhibits of limits of survey with fee proposal. Consultant needs to check curb ramp compliance.
3.3 | Establish property lines, tax id, & ownerships on base map | Yes | X
3.4 | Determine Right of Way Encroachments | Yes | X |  |  |  |  | Encroachment report to be submitted to right of way coordinator
3.5 | Right of Way Plans | Yes | X | X
3.5.1 | ROW Title Sheet | Yes | X |  |  |  |  | Need to follow City General Design Requirements (Needs to be in ODOT plan format)
3.5.2 | Legend Sheet | Yes | X
3.5.3 | Centerline Survey Plat | Yes | X
3.5.4 | Property Map | Yes | X
3.5.5 | Summary of Additional Right of Way | Yes | X
3.5.6 | Detailed ROW Plan Sheets | Yes | X
3.5.7 | Field Review & Verify Property Owners | Yes | X |  |  |  |  | Fifteen days prior to submitting the Final Right of Way Tracings, conduct an in-depth field review of the project and verify property owners. Determine: 1. Any new ownership transactions. 2. Any changes to topographic features, structures, utilities or ownership. 3. Submit legal descriptions to the County Engineer or County Recorder for pre-approval.
3.5.8 | Final Legal Descriptions | Yes | X
3.5.9 | Temporary right of way staking | Yes | X |  | X
4 | Miscellaneous
4.1 | RR Design/Coordination | Likely | X |  |  |  |  | Includes working with the railroad to resolve design issues, and sending copies of the plans to the railroad for review.
4.2 | Prepare FAA Form 7460-1 for Airway/Highway Clearance | Unlikely | X |  | X
4.3 | FEMA Coordination/Permit | Unlikely | X
5 | Calculations
5.1 | Storm Water Management Report | Yes | X |  |  |  |  | Stormwater Design Manual Requirements and inlet spacing design.
5.2 | Lighting Analysis, Voltage Drop Calculations | Yes | X
5.3 | Bridge Design and Analysis | Unlikely | X |  |  |  |  | Bridge Type
5.4 | Structure Rating & Analysis | Unlikely | X
5.5 | Complete bridge hydraulic study and scour analysis | Unlikely | X
6 | Utilities | Yes
6.1 | Subsurface Utility Engineering | Yes | X |  |  |  |  | Quality Level B
6.2 | Subsurface Utility Engineering (potholing) | Yes | X |  | X |  |  | Quality Level A - 10 locates
6.3 | Utility Coordination and Documentation | Yes | X | X |  |  |  | Use Utility coordination log
7 | Geotech and Pavement Design
7.1 | Geotechnical Services and Report | Yes | X
7.2 | Finalize Pavement Section and Design Report | Yes | X |  |  |  |  | Per the City Pavement Design Policy
8 | Public Involvement Process | Yes | X | X
8.1 | Public Involvement meeting - Attendance | Yes | X | X | X |  | Assume 2 public meetings | Preparation, support and attendance for public involvement. Conduct a public meeting to obtain input and concurrence on the planning solution(s) to be carried forward. Prepare for and and conduct the meeting, summarize the results, and respond to all comments generated from the meeting. Develop responses to comments from the Public Involvment meeting for inclusion in the NEPA document.
8.2 | Public Involvement - Preparation of Handouts, comment sheets and sign-in sheets | Yes | X | X | X |  | Assume 2 public meetings | Coordination with City staff in determining the necessary handouts and comment sheets for public involvement. This also includes preparation, printing and delivery of the documents to the public meeting.
8.3 | Preparation of Exhibits | Yes | X |  | X |  | Assume 2 public meetings | Preparation of exhibits necessary for public involvement. This also includes materials and display equipment for the exhibits.
8.4 | Cordination with City Historic Resources Commision and/or Downtown Commission. | Unlikely | X | X | X
9 | Prepare Cost Estimates | Yes | X | X
9.1 | Construction Cost Estimate | Yes | X |  |  |  |  | Construction Cost Estimate shall be submitted with every stage plans per General Design Requirements.
9.2 | Right of Way | Yes | X | X |  |  |  | Consultant to provide acquisition areas and property use only. City to estimate costs.
10 | Preliminary Plan Design | Yes
10.1 | Preliminary Alignment Plan | Yes | X |  |  |  |  | Submittal to be per the General Design Requirements.
10.2 | Conceptual BMP | Yes | X |  |  |  |  | Determine BMP's per the City of Columbus Stormwater Drainage Manual, latest edition.
10.3 | Signal Warrant Analysis | Yes | X |  | X
11 | Plan Design | Yes | X | X | X
11.1 | Title Sheet | Yes | X
11.2 | Schematic | Yes | X
11.3 | Typical Sections | Yes | X |  |  |  |  | Modification to STD DWG 2130 may be necessary. Justification documentation will be required.
11.4 | General Notes | Yes | X
11.5 | MOT Plans | Yes | X
11.6 | SWPPP | Yes | X |  |  |  |  | Consultant should also include fee for NOI and application. Assume City SWPPP policy unless directed to follow ODOT SS832.
11.7 | General Summary | Yes | X
11.8 | Pavement Calculations | Yes | X
11.9 | Plan and Profile | Yes | X
11.10 | Cross Sections | Yes | X
11.11 | Intersection Details | Yes | X |  |  |  |  | Includes curb ramp details
11.12 | Driveway Details | Yes | X
11.13 | Storm Sewer Profiles | Yes | X
11.14 | Culvert Detail Sheets including headwall and wingwall details | Likely | X
11.15 | BMP/Detention Design and Details | Yes | X |  |  |  |  | Quality and Quantity per Stormwater Drainage Manual. This needs to include a maintenance plan.
11.16 | Water Works Plan | Yes | X |  |  |  |  | This could be a separate Water plan.
11.17 | Sanitary Sewer Plans | Yes | X |  |  |  |  | This could be a separate CC plan.
11.18 | Pavement Marking Plan | Yes | X
11.19 | Signing Plan | Likely | X
11.20 | Power/Circuit Layout & Details | Yes | X |  |  |  |  | To include DOP relocation.
11.21 | Lighting Plan and Details | Yes | X
11.22 | Landscape Notes, Plan and Details | Yes | X
11.23 | Signal Plans | [6 empty] | Consulant needs to follow City of Columbus Traffic Signal Design Manual. Include signal kick off meeting in the field with City Signal Staff.
11.23.1 | Signal Plan Sheets | Yes | X
11.23.2 | Wiring diagram & pole orientation | Yes | X |  |  |  |  | SWISS calculations when required for span wire design.
11.23.3 | Timing Chart | Yes | X
11.23.4 | Interconnect Plan and Details | Yes | X
11.24 | Retaining Wall Design and plans | Yes | X |  | X
11.24.1 | Wall Locations | Yes | X |  | X
11.24.2 | Wall Elevations | Yes | X |  | X
11.24.3 | Wall Type | Yes | X | X | X
11.24.4 | Footing/foundation detail | Yes | X |  | X |  |  | Consultant may need to perform additional subsurface investigations and this cost should be included with this item.
11.25 | Bridge Plans
11.25.1 | Site Plan | Unlikely | X
11.25.2 | General Plan | Unlikely | X
11.25.3 | General Notes | Unlikely | X
11.25.4 | Stage Construction Detail Sheets | Unlikely | X
11.25.5 | Abutment Details | Unlikely | X
11.25.6 | Pier Details | Unlikely | X
11.25.7 | Screed Elevations | Unlikely | X
11.25.A | Superstructure
11.25.A.1 | Transverse Section | Unlikely | X
11.25.A.2 | Deck Plan | Unlikely | X
11.25.A.3 | Framing Plan | Unlikely | X
11.25.A.4 | Bearings | Unlikely | X
11.25.A.5 | Girder Details | Unlikely | X
11.25.A.6 | Enddams | Unlikely | X
11.25.A.7 | Camber Diagrams | Unlikely | X
12 | Final Signature Submission | Yes | X
12.1 | Submission of Mylar Title Sheet and documentation | Yes | X |  |  |  |  | Submittal shall be in accordance with the City General Design Requirements.
13 | On-going services during Construction | Yes | X |  | X
13.1 | Pre-Bid Questions | Yes | X |  | X
13.2 | On-going Services During Construction | Yes | X |  | X
13.3 | Shop Drawing Review | Yes | X |  | X
13.4 | As-Builts | Yes | X |  | X
13.5 | Set R/W Pins | Yes | X |  | X |  |  | Consultant should follow City General Design Requirements.